# Tab 1

# PROGRAM CHARTER: Create CHW Navigator

## 1. OVERVIEW

### 1.1 Purpose

Create CHW Copilot, a high-fidelity, auditable pipeline that converts static clinical manuals into validated, platform-agnostic digital decision support. We bridge the gap between paper guidelines and mobile health apps (CHT, OpenSRP, CommCare) used by Community Health Workers (CHWs) and ASHAs.

### 1.2 Objectives

- Understand stakeholder needs: NGO, MOH, CHW, CHW software platforms

Create a product to meet those needs:

- High-Speed Ingestion: Reduce digitization time from months to days via LLM-assisted extraction.

- Formal Verification: Provide mathematical "No-Fail" guarantees: no loops, no gaps, no contradictions.

- Interoperability: Output XLSForms and FHIR Questionnaires that slot directly into existing global health stacks.

- Dignity of Labor: Enhance the professional standing and skills of CHWs through high-quality clinical support.

### 1.3 Strategic Benefits

- For MOHs: Absolute control over clinical logic and an easy path to regulatory approval.

- For CHWs: Real-time, high-quality support that increases local respect and patient outcomes.

- For Platforms: A standardized, validated logic module that eliminates the need for manual coding.

## 2. Scope

### 2.1 Approach: THE PIPELINE (MANUAL-TO-CODE)

The CHW Copilot implements a deterministic pipeline with explicit human-in-the-loop checkpoints:

- AI Ingestion: Automated reading of manuals to find "rough edges" (omissions or ambiguities).

- MOH Addendum: Ministry officials provide clarifications; these become versioned inputs.

- Logic Conversion: Transformation of text into DMN (Decision Model and Notation) and flowcharts.

  - Verification (Formal Methods): Use of prover software to ensure the logic is mathematically sound (No "Dead Ends", etc.).

  - Synthetic Testing: "Synthetic Patients" are run through the logic to ensure the digital output matches clinical intent (DMN = flowchart = input to the prover software).

  - Clinician validation: Clinicians review and approve the decision logic and results of the synthetic patients.

- Code Generation: Compilation of verified logic into XLSForm/FHIR and localized phrase banks.

  - Final Checks:

    - Ensuring the app code behaves exactly like the approved decision trees.

    - CHWs and clinicians approve the phrase bank and translations

### 2.2 In Scope

- Pipeline Software:

  - LLM prompts for most steps of the pipeline

  - Red Teaming: Active "adversarial" testing of prompts and logic to force errors and document repair loops.

    - Lots of quality standards

  - Python-based tools for

    - DMN ↔ Flowchart ↔ XLSForm translation.

    - Formal proofs of no loops, mutually exclusive and collectively exhaustive, etc.

- Stress Testing:

  - Creation of synthetic patients and test harnesses to run them through DMN, flowchart software, prover software and deployable software (XLSForm,e tc.)

  - Use of "Martian Disease" manuals (synthetic diseases) to validate logic engines without clinical bias.

- User Research: Direct engagement with Medic (CHT), Ona (OpenSRP), Dimagi (CommCare), and Indian MOH IT teams.

### 2.3 Out of Scope

- Runtime AI: No LLMs, RAG or non-deterministic AI will run at point of care

- Hardware: We do not provide physical tablets or phones.

### 2.4 ASSUMPTIONS & PRINCIPLES

- Alliance, Not Threat: We assume CHW software platforms will compete to implement this workflow to increase their own value to MOHs.

- MOH will trust our package of validation evidence

- Open Standards: All outputs will be platform-agnostic to prevent vendor lock-in.

- Determinism: Clinical safety requires that for any given patient input, the software must provide the same output every single time.

### 2.5 CONSTRAINTS & RISK MANAGEMENT

| Risk | Mitigation Strategy |
| --- | --- |
| Internal: Resource Volatility (Intern-led programming, and interns get busy) | Modular "Pipeline-as-Code" architecture to allow for asynchronous, independent development. |
| Software: Clinical errors in decision trees that MDs do not catch | Mandatory "Parity Checks" comparing source text to final DMN logic. |
| Software: Language nuance in phrase bank, especially in translation | Creation of "Phrase Banks" that require manual sign-off by local CHW supervisors/ASHAs. |

### 2.6 Potential Impediments

| Potential Impediments | Mitigation Strategy |
| --- | --- |
| Access to MOH/NGO and CHWs to do needs assessment; surveys with the wrong questions get the wrong answers | Work with CHT, Ona, etc. to reach out. |
| Medic.org, Ona, Dimagi, Indian MOH do not integrate | Development of Evidence Packages (flowcharts/proofs/simulated cases) to demonstrate safety |
| MOH/NGO do not adopt due to low trust | Development of Evidence Packages (flowcharts/proofs/simulated cases) to demonstrate safety |
|  | Maybe: We do all the work for existing manuals and hand them sample completed modules |

### Closing Principle

CHW Copilot treats clinical logic as a Public Good. By providing a transparent, verifiable, and open-source pipeline, we ensure that the "brain" of digital health is as reliable as the medicine it supports.

# PROGRAM BREAK-OUT: Projects by team

# Testing Team

- Goals:

  - A validated continuous integration suite that automatically runs all appropriate tests

  - PatientBot ready for CHWs to use, with and without ChatCHW to help

- Activities

  - Create integration tests and end-to-end tests (using XLSForm tools).

  - Ensure sufficient unit tests

  - Create a continuous integration suite that automatically runs all appropriate tests

  - Validate CI suite with good and bad inputs

  - Create PatientBot that can chat with a CHW

### Patient data

- For each module (such as danger signs, diarrhea, cough and fever), pick one, 2 or 3 to fire

- Use the decision tables (DMN) leading to diagnosis.

  - For each observation in a table

    - For each continuous value cutpoint, pick 4 values: missing, just below, equality, and just above (where “below” is defined as less severe, so reverse code MUAC if needed)

      - drop cases where contradict earlier assumptions, such as age ≤ 2 months and age > 6 months.

    - For each Boolean, pick 2 values: missing true and false

      - select all pairs of combinations

  - If the decision table led to a treatment or dosing table:

    - for each continuous value cutpoint, pick 3 values: just below, equality, and just above

    - For each Boolean, pick 2 values: true and false

- Pick one observation with no symptoms

- Pick one observation with every possible symptom

- How big is # observations?

Now rerun that set with every possible toggle, one at a time (e.g, malaria region = true, no RDT = true, etc.).

In each case, store the patient data + correct diagnosis and treatment.

### PatientBot

Run patients using the CHT interface, using existing code for synthetic (simulated) patients / respondents.

Run patients using hard-coded CHT interfaces.

### GraderBot

Compare results from ChatCHW XLSForm and from hard-coded CHT interfaces.